## SSB SBDC
sprint1.Create the initial simple prototype of the Library Assistants Management System website
days in sprint / effort left
Story ID | Issue ID | Status | Assignee | Story/task | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
|  |  |  | Effort Experted (hours) | 57 | 52.9286 | 48.8571 | 44.7857 | 40.7143 | 36.6429 | 32.5714 | 28.5 | 24.4286 | 20.3571 | 16.2857 | 12.2143 | 8.1429 | 4.0714 | 0
|  |  |  | Effort Left (hours) | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  |  |  | Set up continuous integration system
| LAMS-1 | Pending | 谢晓境 | Set up a team box for a CruiseControl.net | 0: 2
| LAMS-2 | Pending | 谢晓境 | Learn the configuration of a CruiseControl.net | 0: 6
| LAMS-3 | Pending | 谢晓境 | Deploy a CruiseControl.net server for the LAMS project on the virtual box | 0: 4
2 |  |  |  | Create application skeleton
| LAMS-4 | Pending | 谢晓境 | Create a asp.net project LAMS on visual studio | bar: 0
| LAMS-5 | Pending | 谢晓境，杨海川 | initiate the asp.net project code and files | 0: 2
3 |  |  |  | Create the LAMS project on the Github
| LAMS-6 | Pending | 谢晓境 | Initial a project on the Github | 0: 3
| LAMS-7 | Pending | 李涛，苏平，陈兵，杨海川，李星懿 | Add product backlog, sprint backlog, SRS., SDS on the wiki of the project | 0: 7
4 |  |  |  | design the basic skeleton of the Library Assistants Management System
| LAMS-8 | Pending | ? | analyse which web pages we should build and each for what | 0: 8
| LAMS-9 | Pending | ? | decide the structure of the database, analyse tables in it | 0: 6
5 |  |  |  | design the home page of the website
| LAMS-12 | Pending | ? | decide what functions should be provided in the home page | 0: 6
| LAMS-13 | Pending | ? | design the structure of the home page,including texts, hyperlinks, images… | 0: 6
| LAMS-14 | Pending | ? | complete the home page's html file | 0: 6